## Progress
Sr. No. | Graphics Name | Stencils Development |  | Static Layout | Query | VW Reply
|  | Static Object | Dynamic Object
1 | 6112C01 | PENDING | PENDING | PENDING
2 | 6112C02 | PENDING | PENDING | PENDING
3 | 6112E02 | PENDING | PENDING | PENDING
4 | 6112F02 | PENDING | PENDING | PENDING
5 | 6112K01 VIBRN | PENDING | PENDING | PENDING
6 | 6112K01 PERM | PENDING | PENDING | PENDING

## Static Object
Sr. No. | Graphics Name | Type | Static Stencil Display | Status
1 | 6112C01 | Column |  | DONE | DONE
2 | 6112C01 | Exchanger |  | DONE | WORKING
3 | 6112C02 | Column |  | PENDING | PENDING
4 | 6112E02 | Exchanger |  | PENDING | TBD
5 | 6112E02 | Exchanger |  | PENDING
6 | 6112E02 | Exchanger |  | PENDING
7 | 6112F02 | Heater |  | PENDING
8 | 6112K01 VIBRN | Electric Motor |  | PENDING
9 | 6112K01 VIBRN | compressor |  | PENDING
10 | 6112K01 VIBRN | compressor |  | PENDING

## Stencils_Dynamic Object
Sr. No. | Object Type | Stencils for Dynamic Object | Assumption/Stencil details | Status
1 | Transmitter |  |  | Pending
2 | PID Controller |  |  | Pending | Done
3 | Alarms |  |  | Pending | Working
4 | Pumps |  |  | Pending | Pending
5 | Control Valve |  |  | Pending | TBD
6 | Bateery Limit |  |  | Pending
7 | ON/OFF valve |  |  | Pending
8 | Pressure Control Valve |  |  | Pending
9 | Hand Switch |  |  | Pending
10 | Pressure Controller |  |  | Pending
11 |  |  |  | Pending
12 | PID controller |  |  | Pending
13 | Alarms |  |  | Pending